## Product Backlog
| Scrum No. | User story/Task | Estimated Time | Priority | Assigned to | Remarks
Sprint 1 | Epic-1 | System Requirement Analysis
| 80 | Create SRS Document | 3 | High | Guruprasad
| Epic-2 | Database Design
| 23 | Create ER Diagram | 3 | High | Samhitha p | Strong and weak entities, and cardinality of relations marking were, left, later completed
| 24 | Create entitiies and select attributes | 2 | High | Samhitha p | Entity-Attributes were re-designed to optimize
| 77 | Logical Design and Normalization | 2 | Low | Fayaz Uddin | Redundancies were removed.
Sprint 2 | Epic-3 | User Management
| 7 | User Registration/ Sign Up | 3 | Low | Anirudha Bhat
| 19 | User login | 4 | High | Anirudha Bhat
| 25 | User Profile Management | 4 | Low | Fayaz Uddin
| Epic-4 | Product Management
| 32 | Add New Product | 3 | High | Guruprasad
| 33 | View Product Catalog | 3 | High | Guruprasad
| Epic-5 | Order Management
| 34 | Place an order | 4 | High | Samhitha
| 35 | View Order history | 3 | Low | Samhitha
Sprint 3 | Epic-6 | Payment Management
| 52 | Process Payment | 4
| Epic-7 | Review Management
| 57 | Submit a review | 4 |  | Samhitha
| Epic-8 | Wishlist Management
| 58 | Add product to wishlist | 2 |  | Anirudha Bhat
| 81 | View Wishlist Items | 2 |  | Anirudha Bhat

## Scrum Report
DATE | FAYAZ | GURU PRASAD | ANIRUDH | SAMITHA
30/07/24 | Discussed the case study | Creating SRS | Discussed about attributes | ER Daigram -plot
31/08/24 | Discussed the Sprint planning | Contributes the ER daigram tool | Craeted Sprits plan | UML daigram

## Sprint 1
Backlog Item | Tasks | Assigned to | Est. days of completion | Days of sprint ( 30/7/24- 2/8/24 )
|  |  |  | 1 | 2 | 3
Create a document that contains system requirements, functional and non-functional requirements, system architecture, Use case diagram, activity diagram,etc | Prepare system requirements document | Guruprasad | 3 | Identified scope and stakeholders | Analyze Requirement Specifications | Design Use case and activity diagrams
Database design | Draw ER Diagram | Samhitha | 3 | Add all the tables and attributes | Connect the tables via relations | Add cardinality of relations
| Create Entities and Select attributes | Samhitha | 2 | Select required entities and relations | Select attributes and their contraint properties
| Logical Design and Normalization | Fayaz | 2 |  | Eliminate redundancies | Design normalized database

## Sprint 2
Backlog Item | Tasks | Assigned to | Est. days of completion | Days of sprint ( 2/8/24 - 7-8-24 )
|  |  |  | 1 | 2 | 3 | 4
User registration: The user must be able to register their email, username and password along with storing profile details | Write SQL Queries required to perform registration | Anirudha Bhat | 1
| Desgin and develop front-end | Fayaz Uddin | 3
User login: User enters credentials and system authenticates the same.The system sends error message on wrong credentials and manages secure session on login | Create Login API | Guruprasad | 4
| Write SQL Queries required to fetch credentials for validation | Anirudha Bhat | 1
| Write backend logic | Samhitha | 2
User Profile Management: The user musr be able to view and edit his personal information. The system must validate the changes and update database. | Write SQL Queries required to fetch and update the database | Anirudha Bhat | 2
| Desgin and develop front-end | Fayaz Uddin | 4
Add New product : Admin can enter product details (name, description, price, category, stock quantity, SKU, brand, weight, dimensions, image URL). Product information is stored securely in the database. | Write SQL Queries to update the database with new product | Anirudha Bhat | 1
| Desgin and develop front-end | Fayaz Uddin | 2
View Product Catalog : User can see the available products and can search for desired product using filters | Decide on the filtering attributes. | Guruprasad | 1
| Write SQL Queries required to fetch product details from the catalog | Anirudha Bhat | 3
| Write backend logic for filters. | Samhitha | 3
Place an order: The user mus be able to add products to the cart. The user must be allowed to enter and store order details such as billing and shippng address, email, etc. | Develop algorithm to process the order and update database accoridingly | Guruprasad | 4
| Write SQL Queries to add order details or update them to the database | Anirudha Bhat | 2
View Order history: User must be able to see their order history, along with the respective order detaiils | Write SQL Queries required to fetch order details | Samhitha | 1
| Method to process and render the order details | Fayaz Uddin | 3

## Sprint 3
Backlog Item | Tasks | Assigned to | Est. days of completion | Days of sprint ( 6/8/24 - 9/8/24 )
|  |  |  | 1 | 2 | 3 | 4
Process Payment: Display payment summary such as total amount, discount, and allows user to select payment method. Updates database on transaction completion and sends proof of payment to user. | Develop a payment page, with required APIs | Fayaz Uddin | 4 | Find best suited API | Design and develop payment page | Consume API | Test and implement payment feature
| Write query to process payment, fetch payment details of the order, and save transaction details in DB | Anirudha Bhat | 2 |  |  | Fetch payment details from DB | Update transaction info in database
| Display and save proof of transaction | Samhitha | 2 |  |  | Fetch transaction details from DB | Display the data in a vuew
Submit product review | Add rating icon | Guruprasad | 2 | Add rating icon feature in web page | Pass the rating to backend
| Add comment section and feedback form | Guruprasad | 3 | Add Comment section on product's view | Store the comments | Add feedback form for each order of a product
| Save rating, review and feedbacks in database | Anirudha Bhat | 2 |  |  | Save the stored comments and feedbacks in Database | Save the stored comments and feedbacks in Database
Add products to wishlist | Provide add to wishlist button in Product's view | Samhitha | 2
| Add to Cart option in Wishlist | Samhitha | 2
View Products in wishlist | SQL Query to fetch WishlistItems | Anirudha Bhat | 2
| Show Product details and Summary price of wishlist | Fayaz Uddin | 1